ECP-2008-DILI-538025

JUDAICA Europeana

Report on the digitisation of the resources provided by partners (final version)

| Deliverable number | D3.6 |
| --- | --- |
| Dissemination level | Public |
| Delivery date | 31 December 2011 |
| Status | Final |
| Author(s) | Jean-Claude Kuperminc AIU, Rachel Heuberger UB-FFM, Lena Stanley-Clamp, Dov Winer EAJC; Pier Giacomo Sola AMITIE; Elizabeth Selby and Helena Liszka JML, Anastasia Loudarou JMG, Maria-Teresa Natale amd Marzia Piccinino MIBAC, Gilles Rozier Medem-MCY, Zsuzsanna Toronyi MZSML |

eContentplus

This project is funded under the eContentplus programme, 
a multiannual Community programme to make digital content in Europe more accessible, usable and exploitable.

Table of Contents

1.	Introduction	3

1.1	The Purpose of Work Package 3	3

1.2	Overview of the deliverable	3

2.	Supporting the Partners in digitising and ingesting their resources	5

2.1	Presentations concerning the Digitisation Work Flow at the Consortium Meetings	5

2.2	Digitisation resources and guidelines	5

2.3	Tools available from the IMPACT (Improving Access to Text) Project	6

3.	The Ingestion Process	7

3.1	Presentation of Ingestion Workflow	7

3.2	The Ingestion Plan	7

3.3	The Ingestion Report	9

4.	Conclusions	10

Annex 1: The Judaica Europeana Ingestion Plan	11

# 1.	Introduction

## 1.1	The Purpose of Work Package 3

Judaica Europeana has documented the Jewish contribution to the European urban development by identifying content related to the Jewish presence and heritage in the cities of Europe. It  works together with European institutions to provide access to a large quantity of European Jewish  heritage at the level of the digital cultural object.

In this context, Work Package 3 (WP3) of the Judaica Europeana project has been tasked with identifying technical tools required for Judaica tasks and  providing support for Partners and Associated Partners. It includes support for:

- The digitisation process and issues concerning hardware, software, file formats, design and presentation, storage.

- Content enrichment facilities through a metadata entry system

- Advanced web management facilities based on open source CMS and associated DBMS supporting mash-up from the EUROPEANA open API.

- Semantic interoperability including the representation of controlled vocabularies in RDF/SKOS.

- Selection, installation and support for the use of an open source knowledge management package.

WP3 has been in constant cooperation with other work packages in the project. In particular WP3 has worked closely with WP2 and WP4: receiving information about standards for their work by WP 2 and feeding information on digitization of the resources and on IPR issues for use within WP4.

WP3 is coordinated by partner 3 AIU. It has been closely supported with technical capabilities provided by partner 6 MiBAC, its partners in the ATHENA project and its contractors and Partner  11 NTUA (National Technical University of Athens). Partner 10 BL (British Library) has contributed to the work of this package by bringing in particular its expertise as coordinator of the sub-project Operational Context in IMPACT for cutting-edge mass digitization technologies.

## 1.2	Overview of the deliverable

The present deliverable is a follow-up to the D3.1. Report on the digitisation of the resources provided by partners (First version) and refers to the content and annexes delivered in that report.

This deliverable documents the work carried out concerning the following tasks:

T3.1 Digitisation processing:

- Supporting the Partners in digitising the resources in their physical collections selected under the thematic domain. WP3  provided support on workflow planning, hardware and software selection, file formats, design and presentation and storage.

T3.2 Metadata, object surrogate, harvesting and search support

- Adapting the metadata entry system of partners for the requirements of EUROPEANA (content enrichment) and when required by one or more partners to provide and install such system from scratch.

- Assuring that the digital object surrogates and the metadata are compliant with the technical requirements guidelines to Europeana: preparation of thumbnails; the provision of identifiers; the access to the digital objects (ftp), the character sets used for the contents of the digital objects; data transfer based on XML structured files; enabling the harvesting of the metadata records via OAI-PMH; supporting the integration of available protocols for search of the collections to those supported by EUROPEANA.

The Judaica content providing partners (six out of eleven) have carried out their digitization programmes with the help of local contractors or in–house facilities. The contractors have been selected in competition with other contractors to provide the most cost-efficient solution. A summary description of these  procedures is available in the DoW section 11.2.2.  Work Package 3 has oriented its partners and in particular those partners taking first steps in the process of digitisation of their holdings to a number of good practice guidelines in this area. This deliverable  describes briefly the steps taken by the partners in the process of digitization. They  included presentations at the consortium meetings for the benefit of the partners;  the gathering of  relevant digitisation guidelines; and the involvement of the British Library team associated with the IMPACT project (Improving Access to Text) for support of interested partners.

# 2.	Supporting the Partners in digitising and ingesting their resources

## 2.1	Presentations concerning the Digitisation Work Flow at the Consortium Meetings

At the first consortium meeting in London in January 2010, Jean-Claude Kuperminc (AIU) and Dov Winer (EAJC)  presented and discussed with the partners the digitisation workflow as part of the review of the WP3 tasks.

At the second consortium meeting held in London (May 2010) Jean-Claude Kuperminc and David Klein (AIU) reviewed in detail the digitisation workflow. They focused on a specific example of a digitisation project dealing with periodicals.

At the same consortium meeting (May 2010), Aly Conteh and Neil Fitzgerald from the British Library presented  the IMPACT project and explained how it can support the digitisation processes undertaken by Judaica Europeana project. They focused on the Decision Support Tools that IMPACT was expected to issue in the coming months.  The purpose of these tools is to initiate, organise, manage and cost mass digitisation projects.

They reviewed other technical developments in the project that were of interest to the partners. Some of the partners expressed interest in using advanced OCR applications that the project developed anchored in products they already use, provided by ABBYY Production, one of the IMPACT partners. This referred mainly to Gothic German characters and Hebrew.

The above presentations and documentation have been shown in the Annexes to the D3.1 Deliverable.

## 2.2	Digitisation resources and guidelines

WP3 has carried out a survey of relevant resources that assisted the partners in the planning and execution of their digitisation workflow. This documentation has been provided in the Deliverable D3.1 Report on the digitisation of the resources provided by partners (First version).

Many relevant resources have been identified. Here we wish to mention the work carried out by the MINERVA project that provided several such documents. (MINERVA was led by MiBAC, the Italian Ministry of Culture and one of the Judaica Europeana partners.) In spite of the fact that the last of these documents was published in 2008, the authors were available for providing advice to Judaica Europeana partners.

The Digitisation Guidelines of the CALIMERA project are available in all European languages. Despite having been published in 2006, they provide a comprehensive view of the process, not limited only to strictly technical aspects but covering also social and managerial issues.

Other guidelines, in particular those maintained by JISC Digital, NISO and the University of Maryland are more recent and constantly updated.

The project IMPACT offers a cutting edge set of tools for advanced digitisation projects. They will be described in the next section. As we mentioned, a leading partner of IMPACT is the British Library and as WP3 participants they were available  to Judaica Europeana partners for advice.

## 2.3	Tools available from the IMPACT (Improving Access to Text) Project

Apart from the clearly defined technical objectives IMPACT has also an important strategic objective: to support all European players such as libraries, cultural institutions, but also companies, decision making bodies and funding agencies with high-level information concerning the mass digitisation and transformation of historical texts.

These objectives are addressed through the following resources:

- A set of Decision Support Tools that can be used to initiate, organise, manage and cost mass digitisation projects.

- A learning resource toolbox that will contain operational guidelines, providing guidance on real world implementation of all tools produced within the project.

- Training and support: an established Help Desk system that will broker end-user requests to project partners and to other digitisation centres of competence. An established training programme dealing with large-scale digitisation issues and technologies, with a range of supporting documentation made available through the project website.

For a review of the available IMPACT Decision Support Tools see the presentation by Neil Fitzgerald (British Library) at:	
http://www.impact-project.eu/uploads/media/Neil_Fitzgerald_Decision_Support_Tools_01.pdf

Metadata for Text Digitisation & OCR

- IMPACT Best Practice Guide: Metadata for Text Digitisation & OCR	671 K	
http://www.impact-project.eu/uploads/media/IMPACT-metadata-bpg-pilot-1.pdf

OCR for Mass Digitisation

- IMPACT Briefing Paper: OCR 148 K	
http://www.impact-project.eu/uploads/media/IMPACT-ocr-bp-pilot-1b.pdf

- IMPACT Best Practice Guide: OCR Section 1 	253 K	
http://www.impact-project.eu/uploads/media/IMPACT-ocr-bpg-pilot-s1.pdf

- IMPACT Best Practice Guide: OCR Section 2 	820 K	
http://www.impact-project.eu/uploads/media/IMPACT-ocr-bpg-pilot-s2.pdf

- IMPACT Best Practice Guide: OCR Section 3 	157 K	
http://www.impact-project.eu/uploads/media/IMPACT-ocr-bpg-pilot-s3.pdf

IMPACT Storage Estimator (ISE)

- IMPACT Storage Estimator 637 K	
http://www.impact-project.eu/uploads/media/IMPACT_Storage-Estimator_BSB_version3_01.xls

- IMPACT Storage Estimator - Tutorial	1.1 M	
http://www.impact-project.eu/uploads/media/IMPACT-isa-tutorial.pdf

# 3.	The Ingestion Process

## 3.1	Presentation of Ingestion Workflow

This section illustrates how the ingestion process was carried out within the JUDAICA EUROPEANA project and how cooperation functioned among the JUDAICA EUROPEANA content providing and technical partners.

WP 3 main tasks were:

- acting as a bridge between the content providing partners and the coordination of the project;

- updating the list of the collections to be provided to JUDAICA EUROPEANA;

- managing the involvement of new content providers;

- reporting about the JUDAICA EUROPEANA activities to WP4 for further dissemination.

Figure 1 – Work Package 3: Coordination of Ingestion and Workflow

WP3 provided support to all content provider partners through AIU which guided them in the mapping process and NTUA which dealt with the ingestion process. The WP3 content management team had the role of interacting with the  Europeana Ingestion Team (FIG. 1).

While the museums, archives and some libraries such as the Alliance Israelite Universelle, (consisting of archives and library), Medem, Centre Français des Musiques Juives were ingesting with the help of the ATHENA/Judaica tool into EUROPEANA, the Frankfurt University Library was ingesting directly into EUROPEANA via Repox.

## 3.2	The Ingestion Plan

During the period January-December 2010 the content providers were asked to fulfil the first important tasks related to WP3: the completion of the standard questionnaire for reporting on the digitisation of the resources provided by the partners, first version (month 12).

The need to further investigate the state of the art of the JUDAICA EUROPEANA digital collections for the definition of the ingestion plan and the compilation of a report about the standards applied by the  museums, libraries and archives, as well as for retrieving information for the other WPs activities (IPR, multilingualism, geo-localisation) were the background of the survey that was launched.

This aims of the survey were to obtain a clear overview on the standards applied by the participant institutions in order  to  construct the JUDAICA EUROPEANA ingestion workflow, and verify the relevant information for the fields of the ingestion plan (e.g. the  name of the collection, the type of digital object – text, image, audio, video - the quantity of thumbnails or samples to be sent to Europeana, whether the metadata are aggregated by anyone else, etc.).

All content providing partners completed the questionnaire  about their collections. The analysis of the technical standards was presented in D2.3 Audit Report on Judaica content including metadata, updated and final version (month 18).

Subsequently, WP3 team developed the Judaica Ingestion Plan: an extract is shown below. For a copy of the full document see Annex 1.

Figure 2: A snapshot of Judaica Europeana Ingestion Plan

The core information given in the Ingestion Plan includes:

- Name of provider

- Data sets:  name,  amounts and type of objects provided : to monitor DoW targets

- Amounts of metadata

- Technical staff contact details

- Ingestion tool to be used

The Ingestion Plan was reviewed and updated at intervals.

## 3.3	The Ingestion Report

As ingestion progressed a Report was compiled and updated to record the data relating to ingested content. Figure 3 below provides quantities per type of object:

| Judaica content by Provider | Text/ Book pages | Text/ Press pages | Text/ Image | Text Archives | Photos/ images | Sound/ Records | Video | Film | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UBFFM, Frankfurt | 969108 | 665975 |  |  |  |  |  |  |  |
|  | 123277 |  |  |  |  |  |  |  |  |
|  | 29166 |  |  |  |  |  |  |  |  |
|  | 72502 |  |  |  |  |  |  |  | 1860028 |
| AIU, Paris |  |  | 50226 | 619236 | 8069 |  | 7 | 16 |  |
|  |  |  | 35410 |  |  |  |  |  |  |
|  |  |  | 25072 |  |  |  |  |  | 738036 |
| Medem Library, Paris | 210000 | 13668 | 168971 |  |  | 690 |  |  |  |
|  |  | 20000 |  |  |  | 3536 |  |  | 416865 |
| CFMJ, Paris |  |  |  |  |  | 14045 |  |  | 14045 |
| JML, London |  |  | 14836 |  |  |  | 149 |  | 14985 |
| Akadem, Paris |  |  |  |  |  |  | 1849 |  | 1849 |
| JHM, Amsterdam |  |  |  |  | 13750 |  |  |  | 13750 |
| Hungarian Jewish Archives, Budapest |  |  | 5584 |  | 2002 |  |  |  | 7586 |
| JHI, Warsaw |  |  |  | 319848 |  |  |  |  | 319848 |
| JMG, Athens |  |  | 18019 |  | 7759 |  | 8 |  | 25786 |
| Sephardi Museum, Toledo | 142 |  |  |  |  |  |  |  | 142 |
| MiBAC, Palatina Library, Parma | 58128 |  |  |  |  |  |  |  | 58,128 |
| MiBAC, Venice State Archives |  |  |  | 40,000 |  |  |  |  | 40,000 |
| Total | 1462323 | 699643 | 318118 | 979084 | 31580 | 18271 | 2006 | 16 | 3.511,048 |

Figure 3 – The Ingestion Report shows the quantities per type of object and content provider.

# 4.	Conclusions

The Judaica Europeana partners have carried out the digitisation of their collections for Judaica Europeana. One of the WP3 tasks was to support the partners in their digitisation work.  Aspects and challenges of digitisation were presented and discussed in the project consortium meetings.

WP3 assembled a list of guidelines and other resources for digitization.  It also identified projects and resources that supported partners in their work. Such resources were available among Judaica Europeana partners like MiBAC (the Italian Ministry of Culture), who led the MINERVA network of projects and the British Library, a leading partner in the IMPACT – Improving Access to Text project.

WP3 developed a coordination model and workflow, the Ingestion Plan and the Ingestion Report which supported the process of ingestion.

The Alliance Israelite Universelle technical staff guided and supported content providers in the mapping and ingestion process. The National Technical University of Athens (NTUA), who joined the project as technical partners in 2011 by amendment to the Grant agreement, provided the necessary additional expertise and fulfilled a key role in the ingestion of content supplied by the project partners, and their semantic interoperability with Europeana requirements .

# Annex 1: The Judaica Europeana Ingestion Plan

| Main contact for ingestion planning (name/e-mail): Rachel Heuberger r.heuberger@ub.uni-frankfurt.de |
| --- |
| Data Provider name | Data Provider country | Dataset(s) | When can be harvested? | Amount of metadata records (with a link to the digital object online) | Technical contact person's email | Ingestion tool |
| University Library Frankfurt | Germany | Freimann-Collection 5500 books / 750000 pages | online | 6.212 | m.knepper@ub.uni-frankfurt.de | Repox |
| University Library Frankfurt | Germany | Yiddish Prints 735 books-collect. / 200000 pages | sent | 748 | m.knepper@ub.uni-frankfurt.de | Repox |
| University Library Frankfurt | Germany | Compact Memory 700000 pages | November | 50.000 | m.knepper@ub.uni-frankfurt.de | Repox |
| University Library Frankfurt | Germany | Frankfurt collection 1000 books-collect. / 200000 pages | sent | 247 | m.knepper@ub.uni-frankfurt.de | Repox |
| University Library Frankfurt | Germany | Frankfurt collection 1000 books-collect. / 200000 pages | October 2nd week | 750 | m.knepper@ub.uni-frankfurt.de | Repox |
| University Library Frankfurt | Germany | Hebrew Manuscripts 350 Manuscripts /75.000 pages | sent | 403 | m.knepper@ub.uni-frankfurt.de | Repox |
| Main contact for ingestion planning (name/e-mail): Anastasia Loudarou aloudarou@jewishmuseum.gr |
| Data Provider name | Data Provider country | Dataset(s) | When can be harvested? | Amount of metadata records (with a link to the digital object online) | Technical contact person's email | Ingestion tool |
| The Jewish Museum of Greece | Greece | Books | September | 648 | AMS-Athens Microfilm Services Mr. Dinos Sarimveis info@scanning.gr | Athena |
| The Jewish Museum of Greece | Greece | Book pages | sent | 2545 | AMS-Athens Microfilm Services Mr. Dinos Sarimveis info@scanning.gr | Athena |
| The Jewish Museum of Greece | Greece | Documents | November | 2765 | AMS-Athens Microfilm Services Mr. Dinos Sarimveis info@scanning.gr | Athena |
| The Jewish Museum of Greece | Greece | Post cards | September | 35 | AMS-Athens Microfilm Services Mr. Dinos Sarimveis info@scanning.gr | Athena |
| The Jewish Museum of Greece | Greece | Ephemera | September | 99 | AMS-Athens Microfilm Services Mr. Dinos Sarimveis info@scanning.gr | Athena |
| The Jewish Museum of Greece | Greece | Etchings | October 1st week | 94 | AMS-Athens Microfilm Services Mr. Dinos Sarimveis info@scanning.gr | Athena |
| The Jewish Museum of Greece | Greece | Contemporary Art Collection | September | 47 | AMS-Athens Microfilm Services Mr. Dinos Sarimveis info@scanning.gr | Athena |
| The Jewish Museum of Greece | Greece | Coins/Medals | September | 125 | AMS-Athens Microfilm Services Mr. Dinos Sarimveis info@scanning.gr | Athena |
| The Jewish Museum of Greece | Greece | Architectural Elements | October 1st week | 27 | AMS-Athens Microfilm Services Mr. Dinos Sarimveis info@scanning.gr | Athena |
| The Jewish Museum of Greece | Greece | Hidden Children | October 2nd week | 294 | AMS-Athens Microfilm Services Mr. Dinos Sarimveis info@scanning.gr | Athena |
| The Jewish Museum of Greece | Greece | Jewish Neighbourhoods | October 2nd week | 94 | AMS-Athens Microfilm Services Mr. Dinos Sarimveis info@scanning.gr | Athena |
| The Jewish Museum of Greece | Greece | Young people in Maelstrom | October 2nd week | 420 | AMS-Athens Microfilm Services Mr. Dinos Sarimveis info@scanning.gr | Athena |
| Main contact for ingestion planning (name/e-mail): Marzia Piccininno marzia.piccininno@beniculturali.it |
| Data Provider name | Data Provider country | Dataset(s) | When can be harvested? | Amount of metadata records (with a link to the digital object online) | Technical contact person's email | Ingestion tool |
| Palatina Library of Parma | Italy | Incunabula - 81 books 16th Century Books - 69 books | October (3rd week) | 150 metadata of books and manuscripts | Antonio Davide Madonna davide.madonna@beniculturali.it | Judaica |
| Archivio di Stato di Venezia | Italy | 1. Jewish Welfare - Registers 1581-1799 - 9 registers | Starting mid November | 40000 | Antonio Davide Madonna davide.madonna@beniculturali.it | Judaica |
|  |  | 2. Regulations for Jews 1516-1799 - 3 files | Starting mid November |  |  | Judaica |
|  |  | 3. Jews- 1750-1796 - 20 files + 1 register | Starting mid November |  |  | Judaica |
|  |  | 4. Documents on Jews 1705-1795 - 26 files= 1 + 55 registers | Starting mid November |  |  | Judaica |
|  |  | 5. Ghetto 1587-1647 - 1 register + 1 file | Starting mid November |  |  | Judaica |
|  |  | 6. Jewish Necrology - 3 registers | Starting mid November |  |  | Judaica |
|  |  | 7. Ghetto 1661-1740 - 4 registers | Starting mid November |  |  | Judaica |
|  |  | 8. Politics towards Jews - 13 registers | Starting mid November |  |  | Judaica |
| Main contact for ingestion planning (name/e-mail): Jean-Claude Kuperminc biblio@aiu.org |
| Data Provider name | Data Provider country | Dataset(s) | When can be harvested? | Amount of metadata records (with a link to the digital object online) | Technical contact person's email | Ingestion tool |
| Alliance Israelite Universelle (AIU) | France | Archives AIU pre-1940 Metadata XML/EAD Archives France, Grèce, Turquie, Hongrie, Italie, Roumanie, Turquie, Yougoslavie 355 reels 710 000 pages | November 1 st week | 3031 | kleido@free.fr | ? |
| Alliance Israelite Universelle (AIU) | France | Archives AIU pre-1940 Metadata XML/EAD Archives Angleterre, Autriche, Bulgarie, Grèce, Hongrie, Roumanie, Turquie, Suisse 69995 pages | October 4th week | 1417 | kleido@free.fr | ? |
| Alliance Israelite Universelle (AIU) | France | Books Metadata MARC21 222 vol. + 29 photos 30340 pages | sent | 251 | kleido@free.fr | Repox |
| Alliance Israelite Universelle (AIU) | France | Books Metadata MARC21 100 vol. + 170 photos | October 4th week | 251 | kleido@free.fr | Repox |
| Alliance Israelite Universelle (AIU) | France | Books Metadata MARC21 284 vol. + 226 photos 47000 pages | online | 486 | kleido@free.fr | Repox |
| Alliance Israelite Universelle (AIU) | France | Photographs Metadata DC 5000 images | October 2nd week | 5000 | kleido@free.fr | Repox |
| Alliance Israelite Universelle (AIU) | France | Periodicals 74 vol. 3898 pages | sent | 74 | kleido@free.fr | Repox |
| Alliance Israelite Universelle (AIU) | France | Periodicals 22 vol. 1140 pages | September 2011 | 22 | kleido@free.fr | Repox |
| Alliance Israelite Universelle (AIU) | France | Periodicals 263 vol, 18150 pages | October 1st week | 263 | kleido@free.fr | Repox |
| Main contact for ingestion planning (name/e-mail): Zsuzsanna Toronyi toronyizsuzsanna@gmail.com |
| Data Provider name | Data Provider country | Dataset(s) | When can be harvested? | Amount of metadata records (with a link to the digital object online) | Technical contact person's email | Ingestion tool |
| Hungarian Jewish Archives | Hungary | Dohany Street Synagogue-Pews | mid October | 2874 | lkasziba@2kal.hu | Judaica |
| Hungarian Jewish Archives | Hungary | Jews of Pest - Conscription | mid October | 662 | lkasziba@2kal.hu | Judaica |
| Hungarian Jewish Archives | Hungary | Family trees | mid November | 120 | lkasziba@2kal.hu | Judaica |
| Hungarian Jewish Archives | Hungary | Photos | end November | 600 | lkasziba@2kal.hu | Judaica |
| Hungarian Jewish Archives | Hungary | Postcards | Sep.2011 | 2000 | lkasziba@2kal.hu | Judaica |
| Main contact for ingestion planning (name/e-mail): Elizabeth Selby elizabeth.selby@jewishmuseum.org.uk |
| Data Provider name | Data Provider country | Dataset(s) | When can be harvested? | Amount of metadata records (with a link to the digital object online) | Technical contact person's email | Ingestion tool |
| Jewish Museum London | United Kingdom |  | sent | 14836 |  | Athena |
| Jewish Museum London | United kingdom |  | November 1 st week | 600 (these content to be digitised) |  | Athena |
| Jewish Museum London | United Kingdom | Audio files | mid November | 150 |  | Athena |
| Main contact for ingestion planning (name/e-mail): Aartjan Nooter aartjan@jhm.nl |
| Data Provider name | Data Provider country | Dataset(s) | When can be harvested? | Amount of metadata records (with a link to the digital object online) | Technical contact person's email | Ingestion tool |
| Joods Historisch Museum | The Netherlands |  | sent | 14020 | Aartjan Nooter aartjan@jhm.nl | Athena |
| Main contact for ingestion planning (name/e-mail): Agnieszka Reszka areszka@jhi.pl |
| Data Provider name | Data Provider country | Dataset(s) | When can be harvested? | Amount of metadata records (with a link to the digital object online) | Technical contact person's email | Ingestion tool |
| Jewish Historical Institute | Poland | Jewish Community of Wrocław (1744-1942), 314,000 pages | October on a weekly basis | 220000 | Przemysław Jaros pj@kompea.pl | Judaica |
| Main contact for ingestion planning (name/e-mail): María Luisa Martínez-Conde martinez.conde@mcu.es |
| Data Provider name | Data Provider country | Dataset(s) | When can be harvested? | Amount of metadata records (with a link to the digital object online) | Technical contact person's email | Ingestion tool |
| Ministry of Culture Sephardi Museum | Spain | 144 texts | September | 144 | kleido@free.fr | Repox |
| Ministry of Culture Sephardi Museum | Spain | 193 images | Summer 2011 | 193 | kleido@free.fr | Repox |
| Main contact for ingestion planning (name/e-mail): Gilles Rozier gilles@yiddishweb.com |
| Data Provider name | Data Provider country | Dataset(s) | When can be harvested? | Amount of metadata records (with a link to the digital object online) | Technical contact person's email | Ingestion tool |
| Bibliothèque Medem | France | Records of Yiddish songs (sound) | online | 690 | kleido@free.fr | Repox |
| Bibliothèque Medem | France | Records of Yiddish songs (sound) | online | 3536 | kleido@free.fr | Repox |
| Bibliothèque Medem | France | Records of Yiddish songs (sound) | October 2011 | 2300 | kleido@free.fr | Repox |
| Bibliothèque Medem | France | Collection of Yiddish books : Memorial books (Yisker-bikher) from Poland, Ukraine, Lithuania and Bielorussia, history of Jews in Europe, literature about Jews 210 000 pages | online | 874 | kleido@free.fr | Repox |
| Bibliothèque Medem | France | Collection of Yiddish books : Memorial books (Yisker-bikher) from Poland, Ukraine, Lithuania and Bielorussia, history of Jews in Europe, literature about Jews 226000 pages | Monthly batches, starting October 2011 | 1000 | kleido@free.fr | Repox |
| Bibliothèque Medem | France | Photographs of Yiddish writers and other Community activists | September 2011 | 190 | kleido@free.fr | Repox |
| Bibliothèque Medem | France | Photographs of Yiddish writers and other Community activists | Monthly batches, starting October 2011 | 900 | kleido@free.fr | Repox |
| Centre français des musiques juives | France | Records of Jewish Music (sound) | online | 14.045 | kleido@free.fr | Repox |
| Centre français des musiques juives | France | Cassettes, scores and books of Jewish Music | November 2011 | 4.000 | kleido@free.fr | Repox |
| Akadem | France | Video | October 2nd week | 1600 | kleido@free,fr | Repox |

# Footnotes

OJ L 79, 24.3.2005, p. 1.

See Amendment to Agreement 538025 page 6, letter of Commission dated 22 August 2011

http://www.abbyy.com

See D7.4 ‘Report on the integration of the plug-in with the Europeana portal’, pp. 15-33. The ATHENA tool can be reached at the following URL: http://athena.image.ntua.gr/athena (reserved to the ATHENA content providers for the ingestion of their contents).